## Sheet0
Release Version | Id | Reporter | Assigned To | Priority | Severity | Reproducibility | Date Submitted | Updated | Summary | Status | Resolution | Module Name | Sub Module Name
2.93 | 428 | DineshKumar | shiva | normal | Major | always | 2017-12-28 | 2017-12-28 | Contract -> if we click print above the contract listing , Quick view column is displayed . | assigned | open | Contracts
2.93 | 425 | DineshKumar | shiva | normal | Major | always | 2017-12-28 | 2017-12-28 | Student Profile update->Error messages are overlapped with each other for invalid CGPA and Percentage | assigned | open | Student Enrollment
2.93 | 424 | Aishwarya BR | Manikandan | urgent | Critical | sometimes | 2017-12-27 | 2017-12-27 | Not able to accept the call letter by students once approved by officer | assigned | open | FTP
2.93 | 423 | DineshKumar | 563708 | normal | Major | always | 2017-12-27 | 2017-12-27 | Quick View-> Quick view is displayed for the request which is pending with establishment | assigned | open | Contracts | Quick View
2.93 | 421 | DineshKumar | 563708 | urgent | Major | always | 2017-12-27 | 2017-12-27 | Quick View-> unable to select more than one reason. | assigned | open | Contracts | Quick View
2.93 | 420 | DineshKumar | 563708 | normal | Major | always | 2017-12-27 | 2017-12-27 | Quick View-> After the verification , the data table is getting split into two. | assigned | open | Contracts | Quick View
2.93 | 419 | DineshKumar | shiva | normal | Major | always | 2017-12-27 | 2017-12-27 | Contract -> Value in the date field is getting cleared if we select the same value twice | assigned | open | Contracts
2.93 | 418 | DineshKumar | shiva | urgent | Minor | always | 2017-12-27 | 2017-12-27 | Edit student: Alignment issue in Error message which is displayed for Student Photo | assigned | open | Super Admin | Edit Student
2.93 | 417 | DineshKumar | 563708 | normal | Major | always | 2017-12-27 | 2017-12-27 | Quick View-> Functionality is not working in firefox 56.0 | assigned | open | Contracts | Quick View
2.93 | 416 | DineshKumar | Tulika | normal | Major | always | 2017-12-27 | 2017-12-27 | Edit student: Super admin is unable to upload the Resume. | assigned | open | Super Admin | Edit Student
2.93 | 410 | Aishwarya BR | Adhi | high | Major | always | 2017-12-26 | 2017-12-28 | Once student is changed from regular to sandwich, not able to add rop/stipend | feedback | reopened | Regional Admin
2.93 | 408 | Aishwarya BR | Tulika | high | Minor | always | 2017-12-26 | 2017-12-28 | Termination status is unaligned | assigned | open | Contracts Sub Modules | Contract Termination
2.93 | 406 | Aishwarya BR | Tulika | immediate | Minor | always | 2017-12-26 | 2017-12-28 | Increase the font size of the error message in state officer login | assigned | open | Contracts Sub Modules | Contract Termination
2.93 | 405 | karthick | jibi | normal | Minor | always | 2017-12-26 | 2017-12-26 | ROP - Notifications in the dashboard | assigned | open | ROP | ROP approval
2.93 | 404 | DineshKumar | 563708 | urgent | Critical | always | 2017-12-26 | 2017-12-26 | Contract quick View-> Student Certificate is not displayed even though the student is having the valid certificate. | assigned | open | Contracts
2.93 | 401 | Aishwarya BR | Sangeetha | high | Major | always | 2017-12-22 | 2017-12-28 | Once the action is taken by placement officer, the page gets loading and no action can be taken by officer | assigned | open | Contracts Sub Modules | Contract Termination
2.93 | 397 | DineshKumar | Tulika | normal | Major | always | 2017-12-14 | 2017-12-14 | Novation -> For old contracts , they did n't list under pending requests | assigned | open | Contracts Sub Modules | Novation
2.93 | 390 | DineshKumar | shiva | normal | Minor | always | 2017-12-07 | 2017-12-28 | Edit student: Alignment and UI issues | assigned | reopened | Super Admin | Edit Student
2.93 | 388 | DineshKumar | 563708 | normal | Major | always | 2017-12-07 | 2017-12-07 | Edit Student: If the mobile no field is left as empty error message is displayed. | assigned | open | Super Admin | Edit student
2.93 | 387 | DineshKumar | Adhi | normal | Major | always | 2017-12-06 | 2017-12-28 | Contract -> Two print ACRF link is displayed in state officer's listing | feedback | reopened | Contracts
2.93 | 386 | DineshKumar | shiva | normal | Major | always | 2017-12-06 | 2017-12-06 | Contract-> After navigating to create contract page if we click Apprenticeship all the fields are disappearing | assigned | open | Contracts
2.93 | 385 | DineshKumar | Sangeetha | immediate | Critical | always | 2017-12-06 | 2017-12-26 | Contract Creation-> Images are not getting printed in the ACRF form & ACRF notification form | assigned | open | Contracts
2.93 | 376 | karthick | shiva | normal | Minor | always | 2017-12-06 | 2017-12-06 | rel-2.93: Institution approval - officer login: table alignment issues | assigned | open | Institute Approval
2.93 | 374 | karthick | shiva | normal | Minor | have not tried | 2017-12-06 | 2017-12-06 | Rel-2.93: student approval - officer login : View certificates | assigned | open | Student Approval

## Sheet2
Count of Module Name | Column Labels
Row Labels | Critical | Major | Minor | Grand Total
Student Enrollment |  | 1 |  | 1
Contracts | 2 | 8 |  | 10
Contracts Sub Modules |  | 2 | 2 | 4
FTP | 1 |  |  | 1
Institute Approval |  |  | 1 | 1
Regional Admin |  | 1 |  | 1
ROP |  |  | 1 | 1
Student Approval |  |  | 1 | 1
Super Admin |  | 2 | 2 | 4
Grand Total | 3 | 14 | 7 | 24